## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | LANGUAGE SOLUTIONS |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE |  | Roshna Sangle |  |  |  |  | DATE | [6 empty] | 2023-05-03
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | A | 2023-01-09 | 2023-01-16 | 2 | 100% | bar: WEEK 1 M to WEEK 1 F
1.2 | Identifying the functionalities of the Mini Project | B | 2023-01-16 | 2023-01-23 | 2 | 100% | bar: WEEK 2 M to WEEK 2 F
1.3 | Discussing the project topic with the help of paper prototype. | A,B,C | 2023-01-23 | 2023-01-30 | 2 | 100% | bar: WEEK 3 M to WEEK 5 F
1.4 | Designing the Graphical User Interface(GUI) | A | 2023-01-30 | 2023-02-13 | 2 | 100%
1.5 | Presentation I | A,B,C | 2023-02-20 | 2023-02-20 | 1 | 100% | bar: WEEK 5 M to WEEK 6 F
2 | Project Design and Implementation
2.1 | Database Design | A,B,C | 2023-02-27 | 2023-03-13 | 1 | 100% | bar: WEEK 7 M to WEEK 8 F
2.2 | Database Connectivity of all modules | A | 2023-03-13 | 2023-03-27 | 1 | 100% | bar: WEEK 9 M to WEEK 10 F
2.3 | Integration of all modules and Report Writing | A | 2023-03-27 | 2023-04-10 | 1 | 100% | bar: WEEK 11 M to WEEK 12 F
2.4 | Presentation II | A,B,C | 2023-04-20 | 2023-04-20 | 2 | 100% | bar: WEEK 12 M to WEEK 14 F